## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Nandana C S | 2026-02-16 | Retrieved document chunks were not always relevant | Sprint 2 | Self | Logical | 2026-02-17 | Closed | Retrieval relevance improved
2 | Nandana C S | 2026-04-02 | Generated answers lacked proper citations | Sprint 4 | Self | Standards | 2026-04-03 | Closed | Implemented source citation in RAG pipeline for accurate references

## Sheet2
Logical
User Interface
Maintainability
Standards
Others